## PO Dashboard
ProGear Direct — Purchase Order & Inbound Shipment Tracker
Period: Jul – Oct 2024 ¦ 30 POs tracked ¦ Suppliers: 5 ¦ Warehouses: NE · SE · WC
Total POs Issued |  | Total PO Value |  | Delivered & Matched |  | In Transit | Discrepancies
30 |  | $103,775 |  | 8 |  | 9 | 9
Supplier On-Time & Accuracy Performance
Supplier | Location | POs Issued | Delivered | Avg Days vs Expected | Discrepancies | On-Time Rate
Apex Equipment Group | Columbus, OH | 8 | 3 | 0.3 | 1 | 25.0%
Champion Source LLC | Charlotte, NC | 6 | 2 | 4 | 1 | 16.7%
Elite Sport Supply | Dallas, TX | 2 | 2 | -1 | 0 | 100.0%
Pacific Athletic Co. | Portland, OR | 7 | 6 | 1 | 5 | 14.3%
Varsity Sports Mfg. | Chicago, IL | 7 | 4 | 1.8 | 2 | 28.6%
PO Status Summary
Status | Count | % of Total
Delivered & Matched | 8 | 26.7%
Discrepancy — Qty Short | 5 | 16.7%
Discrepancy — Wrong SKU | 4 | 13.3%
In Transit | 9 | 30.0%
Pending Shipment | 4 | 13.3%

## PO Log
PO Number | PO Date | Supplier | Supplier Location | SKU | Product | Destination WH | Qty Ordered | Unit Cost ($) | Total PO Value ($) | Expected Delivery | Actual Delivery | Days vs Expected | Qty Received | Status | Matched to Receipt
PO-2024-1001 | 2024-09-15 | Apex Equipment Group | Columbus, OH | PGD-JUMP | Jump Rope (Speed Cable) | Northeast (NE) | 75 | 6.5 | 487.5 | 2024-10-17 |  |  |  | In Transit | Pending
PO-2024-1002 | 2024-10-02 | Pacific Athletic Co. | Portland, OR | PGD-SBALL | Soccer Ball (Size 5, Match) | Southeast (SE) | 150 | 18.75 | 2812.5 | 2024-11-03 | 2024-11-03 | 0 | 150 | Discrepancy — Wrong SKU | No — Review Required
PO-2024-1003 | 2024-07-28 | Apex Equipment Group | Columbus, OH | PGD-GLOVE | Baseball Glove (Youth 11.5") | West Coast (WC) | 100 | 28 | 2800 | 2024-09-03 |  |  |  | In Transit | Pending
PO-2024-1004 | 2024-07-23 | Pacific Athletic Co. | Portland, OR | PGD-LACR | Lacrosse Stick (Adult Composite) | West Coast (WC) | 200 | 41 | 8200 | 2024-09-01 | 2024-09-06 | 5 | 200 | Delivered & Matched | Yes
PO-2024-1005 | 2024-08-21 | Varsity Sports Mfg. | Chicago, IL | PGD-LACR | Lacrosse Stick (Adult Composite) | Southeast (SE) | 50 | 41 | 2050 | 2024-09-21 | 2024-09-24 | 3 | 50 | Delivered & Matched | Yes
PO-2024-1006 | 2024-07-11 | Pacific Athletic Co. | Portland, OR | PGD-RESIST | Resistance Band Set (5-piece) | West Coast (WC) | 150 | 9.25 | 1387.5 | 2024-08-16 | 2024-08-13 | -3 | 150 | Discrepancy — Wrong SKU | No — Review Required
PO-2024-1007 | 2024-09-30 | Champion Source LLC | Charlotte, NC | PGD-FBHELM | Football Helmet (Youth Medium) | Northeast (NE) | 75 | 52 | 3900 | 2024-10-30 | 2024-11-04 | 5 | 75 | Delivered & Matched | Yes
PO-2024-1008 | 2024-07-03 | Pacific Athletic Co. | Portland, OR | PGD-BBALL | Basketball (Official Size 7) | Northeast (NE) | 75 | 24.5 | 1837.5 | 2024-08-17 | 2024-08-15 | -2 | 57 | Discrepancy — Qty Short | No — Review Required
PO-2024-1009 | 2024-09-18 | Varsity Sports Mfg. | Chicago, IL | PGD-FBHELM | Football Helmet (Youth Medium) | Southeast (SE) | 50 | 52 | 2600 | 2024-10-23 |  |  |  | Pending Shipment | Pending
PO-2024-1010 | 2024-07-26 | Pacific Athletic Co. | Portland, OR | PGD-TENN | Tennis Racket (Intermediate) | Southeast (SE) | 50 | 33.5 | 1675 | 2024-08-31 | 2024-09-01 | 1 | 50 | Discrepancy — Wrong SKU | No — Review Required
PO-2024-1011 | 2024-08-15 | Elite Sport Supply | Dallas, TX | PGD-JUMP | Jump Rope (Speed Cable) | Northeast (NE) | 250 | 6.5 | 1625 | 2024-09-19 | 2024-09-18 | -1 | 250 | Delivered & Matched | Yes
PO-2024-1012 | 2024-08-22 | Elite Sport Supply | Dallas, TX | PGD-FBHELM | Football Helmet (Youth Medium) | West Coast (WC) | 50 | 52 | 2600 | 2024-09-14 | 2024-09-13 | -1 | 50 | Delivered & Matched | Yes
PO-2024-1013 | 2024-08-22 | Champion Source LLC | Charlotte, NC | PGD-FBHELM | Football Helmet (Youth Medium) | Northeast (NE) | 75 | 52 | 3900 | 2024-09-13 |  |  |  | Pending Shipment | Pending
PO-2024-1014 | 2024-07-16 | Apex Equipment Group | Columbus, OH | PGD-YOGA | Yoga Mat (6mm Non-Slip, 6-pack) | Southeast (SE) | 100 | 38 | 3800 | 2024-08-15 | 2024-08-20 | 5 | 100 | Delivered & Matched | Yes
PO-2024-1015 | 2024-07-07 | Champion Source LLC | Charlotte, NC | PGD-BBALL | Basketball (Official Size 7) | West Coast (WC) | 100 | 24.5 | 2450 | 2024-07-29 | 2024-08-01 | 3 | 85 | Discrepancy — Qty Short | No — Review Required
PO-2024-1016 | 2024-08-17 | Apex Equipment Group | Columbus, OH | PGD-JUMP | Jump Rope (Speed Cable) | Southeast (SE) | 200 | 6.5 | 1300 | 2024-09-13 | 2024-09-10 | -3 | 200 | Delivered & Matched | Yes
PO-2024-1017 | 2024-07-30 | Champion Source LLC | Charlotte, NC | PGD-JUMP | Jump Rope (Speed Cable) | Southeast (SE) | 100 | 6.5 | 650 | 2024-08-22 |  |  |  | In Transit | Pending
PO-2024-1018 | 2024-10-06 | Varsity Sports Mfg. | Chicago, IL | PGD-RESIST | Resistance Band Set (5-piece) | Northeast (NE) | 250 | 9.25 | 2312.5 | 2024-11-05 | 2024-11-06 | 1 | 231 | Discrepancy — Qty Short | No — Review Required
PO-2024-1019 | 2024-08-02 | Varsity Sports Mfg. | Chicago, IL | PGD-LACR | Lacrosse Stick (Adult Composite) | Southeast (SE) | 50 | 41 | 2050 | 2024-09-03 |  |  |  | Pending Shipment | Pending
PO-2024-1020 | 2024-08-02 | Apex Equipment Group | Columbus, OH | PGD-TENN | Tennis Racket (Intermediate) | Northeast (NE) | 150 | 33.5 | 5025 | 2024-09-05 | 2024-09-04 | -1 | 136 | Discrepancy — Qty Short | No — Review Required
PO-2024-1021 | 2024-09-24 | Apex Equipment Group | Columbus, OH | PGD-GLOVE | Baseball Glove (Youth 11.5") | West Coast (WC) | 250 | 28 | 7000 | 2024-11-02 |  |  |  | In Transit | Pending
PO-2024-1022 | 2024-08-14 | Apex Equipment Group | Columbus, OH | PGD-RESIST | Resistance Band Set (5-piece) | Northeast (NE) | 50 | 9.25 | 462.5 | 2024-09-19 |  |  |  | In Transit | Pending
PO-2024-1023 | 2024-08-03 | Pacific Athletic Co. | Portland, OR | PGD-FBHELM | Football Helmet (Youth Medium) | West Coast (WC) | 250 | 52 | 13000 | 2024-09-15 |  |  |  | In Transit | Pending
PO-2024-1024 | 2024-08-21 | Apex Equipment Group | Columbus, OH | PGD-RESIST | Resistance Band Set (5-piece) | West Coast (WC) | 50 | 9.25 | 462.5 | 2024-09-18 |  |  |  | In Transit | Pending
PO-2024-1025 | 2024-09-25 | Varsity Sports Mfg. | Chicago, IL | PGD-TENN | Tennis Racket (Intermediate) | Southeast (SE) | 250 | 33.5 | 8375 | 2024-10-23 | 2024-10-23 | 0 | 250 | Discrepancy — Wrong SKU | No — Review Required
PO-2024-1026 | 2024-09-10 | Champion Source LLC | Charlotte, NC | PGD-JUMP | Jump Rope (Speed Cable) | Southeast (SE) | 200 | 6.5 | 1300 | 2024-10-05 |  |  |  | In Transit | Pending
PO-2024-1027 | 2024-07-10 | Varsity Sports Mfg. | Chicago, IL | PGD-SBALL | Soccer Ball (Size 5, Match) | Southeast (SE) | 200 | 18.75 | 3750 | 2024-08-03 | 2024-08-06 | 3 | 200 | Delivered & Matched | Yes
PO-2024-1028 | 2024-09-19 | Champion Source LLC | Charlotte, NC | PGD-RESIST | Resistance Band Set (5-piece) | West Coast (WC) | 250 | 9.25 | 2312.5 | 2024-10-14 |  |  |  | In Transit | Pending
PO-2024-1029 | 2024-07-23 | Varsity Sports Mfg. | Chicago, IL | PGD-JUMP | Jump Rope (Speed Cable) | Southeast (SE) | 100 | 6.5 | 650 | 2024-08-29 |  |  |  | Pending Shipment | Pending
PO-2024-1030 | 2024-09-27 | Pacific Athletic Co. | Portland, OR | PGD-FBHELM | Football Helmet (Youth Medium) | Southeast (SE) | 250 | 52 | 13000 | 2024-11-08 | 2024-11-13 | 5 | 240 | Discrepancy — Qty Short | No — Review Required

## Receipt Log
Receipt # | PO Number | Receipt Date | Warehouse | SKU | Product | Qty Expected | Qty Received | Variance | Unit Cost ($) | Total Value ($) | Match Status | Notes
REC-2024-2002 | PO-2024-1002 | 2024-11-03 | Southeast (SE) | PGD-SBALL | Soccer Ball (Size 5, Match) | 150 | 150 | 0 | 18.75 | 2812.5 | ⚠️ Discrepancy | Wrong SKU delivered — coordinate return with Pacific Athletic Co.
REC-2024-2004 | PO-2024-1004 | 2024-09-06 | West Coast (WC) | PGD-LACR | Lacrosse Stick (Adult Composite) | 200 | 200 | 0 | 41 | 8200 | ✅ Matched
REC-2024-2005 | PO-2024-1005 | 2024-09-24 | Southeast (SE) | PGD-LACR | Lacrosse Stick (Adult Composite) | 50 | 50 | 0 | 41 | 2050 | ✅ Matched
REC-2024-2006 | PO-2024-1006 | 2024-08-13 | West Coast (WC) | PGD-RESIST | Resistance Band Set (5-piece) | 150 | 150 | 0 | 9.25 | 1387.5 | ⚠️ Discrepancy | Wrong SKU delivered — coordinate return with Pacific Athletic Co.
REC-2024-2007 | PO-2024-1007 | 2024-11-04 | Northeast (NE) | PGD-FBHELM | Football Helmet (Youth Medium) | 75 | 75 | 0 | 52 | 3900 | ✅ Matched
REC-2024-2008 | PO-2024-1008 | 2024-08-15 | Northeast (NE) | PGD-BBALL | Basketball (Official Size 7) | 75 | 57 | -18 | 24.5 | 1396.5 | ⚠️ Discrepancy | Short by 18 units — follow up with Pacific Athletic Co.
REC-2024-2010 | PO-2024-1010 | 2024-09-01 | Southeast (SE) | PGD-TENN | Tennis Racket (Intermediate) | 50 | 50 | 0 | 33.5 | 1675 | ⚠️ Discrepancy | Wrong SKU delivered — coordinate return with Pacific Athletic Co.
REC-2024-2011 | PO-2024-1011 | 2024-09-18 | Northeast (NE) | PGD-JUMP | Jump Rope (Speed Cable) | 250 | 250 | 0 | 6.5 | 1625 | ✅ Matched
REC-2024-2012 | PO-2024-1012 | 2024-09-13 | West Coast (WC) | PGD-FBHELM | Football Helmet (Youth Medium) | 50 | 50 | 0 | 52 | 2600 | ✅ Matched
REC-2024-2014 | PO-2024-1014 | 2024-08-20 | Southeast (SE) | PGD-YOGA | Yoga Mat (6mm Non-Slip, 6-pack) | 100 | 100 | 0 | 38 | 3800 | ✅ Matched
REC-2024-2015 | PO-2024-1015 | 2024-08-01 | West Coast (WC) | PGD-BBALL | Basketball (Official Size 7) | 100 | 85 | -15 | 24.5 | 2082.5 | ⚠️ Discrepancy | Short by 15 units — follow up with Champion Source LLC
REC-2024-2016 | PO-2024-1016 | 2024-09-10 | Southeast (SE) | PGD-JUMP | Jump Rope (Speed Cable) | 200 | 200 | 0 | 6.5 | 1300 | ✅ Matched
REC-2024-2018 | PO-2024-1018 | 2024-11-06 | Northeast (NE) | PGD-RESIST | Resistance Band Set (5-piece) | 250 | 231 | -19 | 9.25 | 2136.75 | ⚠️ Discrepancy | Short by 19 units — follow up with Varsity Sports Mfg.
REC-2024-2020 | PO-2024-1020 | 2024-09-04 | Northeast (NE) | PGD-TENN | Tennis Racket (Intermediate) | 150 | 136 | -14 | 33.5 | 4556 | ⚠️ Discrepancy | Short by 14 units — follow up with Apex Equipment Group
REC-2024-2025 | PO-2024-1025 | 2024-10-23 | Southeast (SE) | PGD-TENN | Tennis Racket (Intermediate) | 250 | 250 | 0 | 33.5 | 8375 | ⚠️ Discrepancy | Wrong SKU delivered — coordinate return with Varsity Sports Mfg.
REC-2024-2027 | PO-2024-1027 | 2024-08-06 | Southeast (SE) | PGD-SBALL | Soccer Ball (Size 5, Match) | 200 | 200 | 0 | 18.75 | 3750 | ✅ Matched
REC-2024-2030 | PO-2024-1030 | 2024-11-13 | Southeast (SE) | PGD-FBHELM | Football Helmet (Youth Medium) | 250 | 240 | -10 | 52 | 12480 | ⚠️ Discrepancy | Short by 10 units — follow up with Pacific Athletic Co.

## Discrepancy Report
Discrepancy Report — Items Requiring Follow-Up
Review each discrepancy below and coordinate resolution with the supplier. Update status once resolved.
PO Number | Receipt # | Supplier | SKU | Product | Destination WH | Qty Ordered | Qty Received | Variance | Issue Type | Supplier Contact Action | Resolution Status | Notes
PO-2024-1002 | REC-2024-2002 | Pacific Athletic Co. | PGD-SBALL | Soccer Ball (Size 5, Match) | Southeast (SE) | 150 | 150 | 0 | Wrong SKU delivered — product mismatch | Arrange return shipment; reorder correct SKU | Open — Pending Supplier Response | Wrong SKU delivered — coordinate return with Pacific Athletic Co.
PO-2024-1006 | REC-2024-2006 | Pacific Athletic Co. | PGD-RESIST | Resistance Band Set (5-piece) | West Coast (WC) | 150 | 150 | 0 | Wrong SKU delivered — product mismatch | Arrange return shipment; reorder correct SKU | Open — Pending Supplier Response | Wrong SKU delivered — coordinate return with Pacific Athletic Co.
PO-2024-1008 | REC-2024-2008 | Pacific Athletic Co. | PGD-BBALL | Basketball (Official Size 7) | Northeast (NE) | 75 | 57 | -18 | Quantity short — fewer units received than ordered | Request credit or replacement shipment | Open — Pending Supplier Response | Short by 18 units — follow up with Pacific Athletic Co.
PO-2024-1010 | REC-2024-2010 | Pacific Athletic Co. | PGD-TENN | Tennis Racket (Intermediate) | Southeast (SE) | 50 | 50 | 0 | Wrong SKU delivered — product mismatch | Arrange return shipment; reorder correct SKU | Open — Pending Supplier Response | Wrong SKU delivered — coordinate return with Pacific Athletic Co.
PO-2024-1015 | REC-2024-2015 | Champion Source LLC | PGD-BBALL | Basketball (Official Size 7) | West Coast (WC) | 100 | 85 | -15 | Quantity short — fewer units received than ordered | Request credit or replacement shipment | Open — Pending Supplier Response | Short by 15 units — follow up with Champion Source LLC
PO-2024-1018 | REC-2024-2018 | Varsity Sports Mfg. | PGD-RESIST | Resistance Band Set (5-piece) | Northeast (NE) | 250 | 231 | -19 | Quantity short — fewer units received than ordered | Request credit or replacement shipment | Open — Pending Supplier Response | Short by 19 units — follow up with Varsity Sports Mfg.
PO-2024-1020 | REC-2024-2020 | Apex Equipment Group | PGD-TENN | Tennis Racket (Intermediate) | Northeast (NE) | 150 | 136 | -14 | Quantity short — fewer units received than ordered | Request credit or replacement shipment | Open — Pending Supplier Response | Short by 14 units — follow up with Apex Equipment Group
PO-2024-1025 | REC-2024-2025 | Varsity Sports Mfg. | PGD-TENN | Tennis Racket (Intermediate) | Southeast (SE) | 250 | 250 | 0 | Wrong SKU delivered — product mismatch | Arrange return shipment; reorder correct SKU | Open — Pending Supplier Response | Wrong SKU delivered — coordinate return with Varsity Sports Mfg.
PO-2024-1030 | REC-2024-2030 | Pacific Athletic Co. | PGD-FBHELM | Football Helmet (Youth Medium) | Southeast (SE) | 250 | 240 | -10 | Quantity short — fewer units received than ordered | Request credit or replacement shipment | Open — Pending Supplier Response | Short by 10 units — follow up with Pacific Athletic Co.